## Project Timeline
Vocoder
Binh an Pham, M Rachel Van Pelt, Steven Tran
Vinitha Subburaj
CS 4391
Milestones |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  |  | April |  |  |  | May
|  |  | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31
Project Proposal |  |  | August 3: PROJECT START; May 17: PROJECT END
Project Plan | bar: August 31
Software Requirement Specification | bar: September 7; October 5
Feasibility and Literature Analysis | bar: September 14
Data Flow Diagram | bar: October 5
Software Design Document |  | 1. Intro and Overview | bar: September 28
|  | 2. UI Design | October 5: 2
|  | 3. UML Diagrams | October 5: 3
|  | 4. Architecture | October 12: 4
|  | 5. Data Model and Constraints | October 26: 5
IMPLEMENTATION | Demo Program | bar: October 5
TKinter | bar: October 12
CNV Command | bar: October 12
UI Layout | bar: October 12
Integrate test into UI | bar: October 19
Improve accuracy of voice recognition by finding closest match | bar: October 26
AOV, RS, CFL, CIS Commands | bar: October 26
Adding Google Voice Recognition | bar: October 26
Images to use in UI | bar: November 2; April 19
Adding Terminal Output to UI | bar: November 2
| Voice Training | 1. Record Voice Lines | bar: November 23; Febuary 22; April 5
|  | 2. Train Language Model | December 28: 2
|  | 3. Change Language Model | January 25: 3
Pop Up Windows to help use Commands | bar: December 21
HTML Documentation of Code | bar: January 11
CF Command | bar: January 11
CWL, CEIF, CES, CA Command | bar: January 25
SW, SL, SB Command | bar: Febuary 8; March 8
CUT, CT, PT, UC, RC Command | bar: Febuary 22
File System Functionality | bar: Febuary 1
Line Numbers in UI | bar: March 8
Dark Mode for GUI | bar: March 29
IC, ICHAR Command | bar: March 22
Documentation | bar: January 4; April 19